## Hoja1
wp | activity | start_date | end_date
Public Engagement | 1. Community engagement | 2023-03-27 | 2023-04-10
Brigadas | 1. Drones | 2023-03-27 | 2023-04-10
Brigadas | 2. Ground truth | 2023-03-27 | 2023-04-10
Brigadas | 3. Georeference | 2023-03-27 | 2023-04-10
Salida Rutinaria | 4. Audiomoths | 2023-03-27 | 2023-04-03
Salida Rutinaria | 5. weather stations | 2023-03-27 | 2023-04-03
Salida Rutinaria | 6. Air quality sensors | 2023-03-27 | 2023-04-03
Salida Rutinaria | 4. Audiomoths | 2023-04-10 | 2023-04-17
Salida Rutinaria | 5. weather stations | 2023-04-10 | 2023-04-17
Salida Rutinaria | 6. Air quality sensors | 2023-04-10 | 2023-04-17
Salida Rutinaria | 4. Audiomoths | 2023-04-24 | 2023-05-01
Salida Rutinaria | 5. weather stations | 2023-04-24 | 2023-05-01
Salida Rutinaria | 6. Air quality sensors | 2023-04-24 | 2023-05-01
Salida Rutinaria | 4. Audiomoths | 2023-05-08 | 2023-05-15
Salida Rutinaria | 5. weather stations | 2023-05-08 | 2023-05-15
Salida Rutinaria | 6. Air quality sensors | 2023-05-08 | 2023-05-15
Brigadas | 1. Drones | 2023-05-22 | 2023-06-05
Brigadas | 2. Ground truth | 2023-05-22 | 2023-05-29
Salida Rutinaria | 4. Audiomoths | 2023-05-22 | 2023-05-29
Salida Rutinaria | 5. weather stations | 2023-05-22 | 2023-05-29
Salida Rutinaria | 6. Air quality sensors | 2023-05-22 | 2023-05-29
Salida Rutinaria | 4. Audiomoths | 2023-06-05 | 2023-06- 12
Salida Rutinaria | 5. weather stations | 2023-06-05 | 2023-06- 12
Salida Rutinaria | 6. Air quality sensors | 2023-06-05 | 2023-06- 12
Salida Rutinaria | 4. Audiomoths | 2023-06-19 | 2023-06-26
Salida Rutinaria | 5. weather stations | 2023-06-19 | 2023-06-26
Salida Rutinaria | 6. Air quality sensors | 2023-06-19 | 2023-06-26
Salida Rutinaria | 4. Audiomoths | 2023-07-03 | 2023-07-10
Salida Rutinaria | 5. weather stations | 2023-07-03 | 2023-07-10
Salida Rutinaria | 6. Air quality sensors | 2023-07-03 | 2023-07-10
Salida Rutinaria | 4. Audiomoths | 2023-07-17 | 2023-07-24
Salida Rutinaria | 5. weather stations | 2023-07-17 | 2023-07-24
Salida Rutinaria | 6. Air quality sensors | 2023-07-17 | 2023-07-24
Salida Rutinaria | 4. Audiomoths | 2023-07-31 | 2023-08-07
Salida Rutinaria | 5. weather stations | 2023-07-31 | 2023-08-07
Salida Rutinaria | 6. Air quality sensors | 2023-07-31 | 2023-08-07
Salida Rutinaria | 4. Audiomoths | 2023-08-14 | 2023-08-21
Salida Rutinaria | 5. weather stations | 2023-08-14 | 2023-08-21
Salida Rutinaria | 6. Air quality sensors | 2023-08-14 | 2023-08-21
Salida Rutinaria | 4. Audiomoths | 2023-08-28 | 2023-09-04
Salida Rutinaria | 5. weather stations | 2023-08-28 | 2023-09-04
Salida Rutinaria | 6. Air quality sensors | 2023-08-28 | 2023-09-04
Salida Rutinaria | 4. Audiomoths | 2023-09-11 | 2023-09-18
Salida Rutinaria | 5. weather stations | 2023-09-11 | 2023-09-18
Salida Rutinaria | 6. Air quality sensors | 2023-09-11 | 2023-09-18
Salida Rutinaria | 4. Audiomoths | 2023-09-25 | 2023-10-02
Salida Rutinaria | 5. weather stations | 2023-09-25 | 2023-10-02
Salida Rutinaria | 6. Air quality sensors | 2023-09-25 | 2023-10-02
Salida Rutinaria | 4. Audiomoths | 2023-10-09 | 2023-10-16
Salida Rutinaria | 5. weather stations | 2023-10-09 | 2023-10-16
Salida Rutinaria | 6. Air quality sensors | 2023-10-09 | 2023-10-16
Salida Rutinaria | 4. Audiomoths | 2023-10-23 | 2023-10-30
Salida Rutinaria | 5. weather stations | 2023-10-23 | 2023-10-30
Salida Rutinaria | 6. Air quality sensors | 2023-10-23 | 2023-10-30
Salida Rutinaria | 4. Audiomoths | 2023-11-06 | 2023-11-13
Salida Rutinaria | 5. weather stations | 2023-11-06 | 2023-11-13
Salida Rutinaria | 6. Air quality sensors | 2023-11-06 | 2023-11-13
Salida Rutinaria | 4. Audiomoths | 2023-11-20 | 2023-11-27
Salida Rutinaria | 5. weather stations | 2023-11-20 | 2023-11-27
Salida Rutinaria | 6. Air quality sensors | 2023-11-20 | 2023-11-27
Salida Rutinaria | 4. Audiomoths | 2023-12-04 | 2023-12-11
Salida Rutinaria | 5. weather stations | 2023-12-04 | 2023-12-11
Salida Rutinaria | 6. Air quality sensors | 2023-12-04 | 2023-12-11
Salida Rutinaria | 4. Audiomoths | 2023-12-18 | 2023-12-25
Salida Rutinaria | 5. weather stations | 2023-12-18 | 2023-12-25
Salida Rutinaria | 6. Air quality sensors | 2023-12-18 | 2023-12-25
Salida Rutinaria | 4. Audiomoths | 2024-01-01 | 2024-01-08
Salida Rutinaria | 5. weather stations | 2024-01-01 | 2024-01-08
Salida Rutinaria | 6. Air quality sensors | 2024-01-01 | 2024-01-08
Salida Rutinaria | 4. Audiomoths | 2024-01-15 | 2024-01-22
Salida Rutinaria | 5. weather stations | 2024-01-15 | 2024-01-22
Salida Rutinaria | 6. Air quality sensors | 2024-01-15 | 2024-01-22
Salida Rutinaria | 4. Audiomoths | 2024-01-29 | 2024-02-05
Salida Rutinaria | 5. weather stations | 2024-01-29 | 2024-02-05
Salida Rutinaria | 6. Air quality sensors | 2024-01-29 | 2024-02-05
Salida Rutinaria | 4. Audiomoths | 2024-02-12 | 2024-02-19
Salida Rutinaria | 5. weather stations | 2024-02-12 | 2024-02-19
Salida Rutinaria | 6. Air quality sensors | 2024-02-12 | 2024-02-19
Salida Rutinaria | 4. Audiomoths | 2024-02-26 | 2024-03-04
Salida Rutinaria | 5. weather stations | 2024-02-26 | 2024-03-04
Salida Rutinaria | 6. Air quality sensors | 2024-02-26 | 2024-03-04
Brigadas | 1. Drones | 2023-07-17 | 2023-07-31
Brigadas | 2. Ground truth | 2023-07-17 | 2023-07-24
Brigadas | 1. Drones | 2023-09-11 | 2023-09-25
Brigadas | 2. Ground truth | 2023-09-11 | 2023-09-25
Brigadas | 3. Georeference | 2023-09-11 | 2023-09-25
Brigadas | 1. Drones | 2023-11-06 | 2023-11-20
Brigadas | 2. Ground truth | 2023-11-06 | 2023-11-13
Brigadas | 1. Drones | 2024-01-01 | 2024-01-15
Brigadas | 2. Ground truth | 2024-01-01 | 2024-01-08
Brigadas | 1. Drones | 2024-02-26 | 2024-03-11
Brigadas | 2. Ground truth | 2024-02-26 | 2024-03-11
Brigadas | 3. Georeference | 2024-02-26 | 2024-03-11